## Isotop Planner
Isotop Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
 | time axis 2023-03-30 to 2023-06-07
Decide what to optimize and how | 2023-03-31 | 7 | 2023-03-31 | 7 | 100%
What is comet ML a how to implement it to existing code/repo Complete code for | 2023-04-07 | 7 | 2023-04-07 | 7 | 100%
Complete code for optimization | 2023-04-14 | 7 | 2023-04-14 | 20 | 100%
Complete code for comet ML | 2023-04-14 | 7 | 2023-04-24 | 17 | 100%
Upload Optimization code to Github | 2023-04-21 | 3 | 2023-04-27 | 2 | 100%
Update repo to add comet ML to training and Optimization | 2023-04-21 | 3 | 2023-05-02 | 5 | 100%
Re-structure Github repo | 2023-04-28 | 14 | 2023-05-04 | 7 | 100%
Revise Use cases, user stories , and components | 2023-04-28 | 7 | 2023-05-04 | 7 | 100%
Create user interaction component | 2023-05-12 | 7 | 2023-05-13 | 7 | 100%
Prepare for Presentation | 2023-05-19 | 14 | 2023-06-02 | 3 | 100%
Extra deliverables to be considered if time allows
Generate complex, noisy NMR spectra ( NMRsim?)
Train the model using complex, noisy NMR spectra (Google Colab )
Update repo to reflect the updates on codes
Create the final version of the code and push to repo
Access to real NMR spectra (60 MHz, 400MHz)
Train the model using real experimental NMR spectra (Google Colab )

## What to optimize
Optimize CNN structure | num_layers = trial.suggest_int('num_layers', 3, 7, step=2)
num_channels = trial.suggest_int('num_channels', 32, 128, step=32)
kernel_size = trial.suggest_int('kernel_size', 3, 7, step=2)
drop_out = trial.suggest_float("drop_out", 0.0, 0.5)
Optimize hyperparameter | optimizer_name = trial.suggest_categorical('optimizer', ['Adam', 'Adadelta', 'Adagrad', 'RMSprop', 'SGD'])
lr = trial.suggest_float('lr', 1e-5, 1e-1, log=True)
optimizer = getattr(optim, optimizer_name)(model.parameters(), lr=lr)
batch_size = trial.suggest_int('batch_size', 64, 256, step=64)
Best senario ( in ideal world) | Use a larger search range for structure and hyperparameters. Doing so will exponentially increase the number of trainls tho !!

## Comet ML
from comet_ml import Experiment
# Instantiate the experiment and set the desired options
experiment = Experiment(
api_key="gT6S0qZpb50idSfM01s4q2uQS",
project_name="CNN_model",
workspace="faizaab",
auto_metric_logging=True,
auto_param_logging=True,
log_graph=True,
auto_metric_step_rate=True,
parse_args=True,
auto_histogram_weight_logging=True,
auto_histogram_gradient_logging=True,
auto_histogram_activation_logging=True,
auto_histogram_epoch_rate=True,
)
# train model
model.to(device)
train_loss_epoch, valid_loss_epoch, best_model_ckpt = train_valid_loop(
model, train_dataloader, valid_dataloader, optimizer, criterion, args.num_epochs
)
# Log the custom metrics, parameters, and tags
experiment.log_metric("train_loss", tepoch_loss, step=e)
experiment.log_metric("valid_loss", vepoch_loss, step=e)
experiment.log_metric("avg_valid_loss", best_model_ckpt['avg_valid_loss'])
experiment.log_metric("best_epoch", best_model_ckpt['epoch'])
experiment.log_metric("avg_test_loss", test_epoch_loss)
experiment.log_parameters(dict(name2params[args.model_name]))
experiment.add_tags([args.model_name, f"{args.high_resolution_frequency}MHz"])
Final Conclusion | Comet ML logs experiment parameter, it's not easy or straightforward to try to combine Comet ML with optimization loop

## Re-structure Github repo
The structure and content of the repo should be as follows:
NMR-Upscale-UW/NMR_Upscale_UW_DIRECT
README.md
LICENSE
.gitignore
/isotop
_init__.py
models.py
model_params.py
train.py
optimize.py
dataset.py
setup.py
/script
train.sh
generate_data.sh
/test
_init__.py
test_datasets.py
test_models.py
test_train.py
/notebooks and other
All notebooks, ppt and Gantt chart

## Revise Use cases, user stories
User Stories
1. ML Technician
· Needs to perform periodic updates, be able to read source code, document changes, update ML models with newer more accurate models.
· Technicians may need access to new and original data, so they may be able to validate a newer or existing model if code breaks.
· Tech would need to be able to collaborate effectively with other technicians but keep "secrets" kept secret (Licensing etc?)
· Remote work? How does code security work if not on a local machine
· Be able to validate model performance etc.
· Log in authentication/token
2. Lab Tech
· Patrick is a chemist who has obtained an NMR spectrum that was obtained at a 60 MHz. He needs to upscale the resolution so that the peak resolution is more resolved for analysis.
· Ideally, the NMR Upscaling software would communicate directly with the NMR hardware so that output spectra experimentally taken would be directly inputted into the ML model for upscaling.
· Patrick needs to know labels/selections for the spectrum (what molecule, frequency scaled to, certainty, etc.)
· If not directly imported from NMR hardware, Patrick should have the option to input data himself.
3. Other Software Engineers
· Jane and John are software engineers working on implementing the code into their operating system. It is important that they know what the code does, what each function does, and potential errors that could result from these functions depending on input and output, how to translate the code to a machine-oriented programming language, and analyze bugs that could result from the software or its implementation.
· Annotated code is important.
· Docstrings for functions
· Open source/licensing
4. High-Level Leadership
· Heather is in a high-level leadership position in the organization. It is important that she knows how much time, use, and resources are allocated to the development and maintenance of the software.
· Output data/plots such as (usage per day, model performance and accuracy, and who is logging in to track manpower)
· Statistics and model performance, translated to something readable to someone unversed in ML or NMR
Example Use Cases
1. ML Technician
· Technician receives more experimental data to input in the model
· Prompts to input data
· Able to validate new model performance
2. ML Technician
· Technician finds that a new ML model might be beneficial to the upscaling
· Access to the code and workflow to add, train, and validate new model
· Output successfully is incorporated with the software
3. Lab Tech
· Patrick wants to select what upscaling method he would like to scale to
· Prompted with selections of models trained (100, 200, 300, 400, etc.)
· Software tells him statistical confidence in the results for each
· Patrick then makes the determination of what resolution he is confident and analyzes experimental results
4. Lab Tech
· Patrick has both a 60 MHz and 400 MHz spectrum that he experimentally took
· He wants the option to add the data to a repository for inclusion for model performance
5. Software Engineer
· The software the engineer is working on has been updated and can no longer input or output spectral data
· The engineer needs access to the code so they can work on changes to incorporate it in the new updates
· The engineer is prompted with a authentication key to open and work on the code
· Upon entering the key, they can access and work on changes
Component Design and Ideas ( this needs to be reviewed and rewritten)
1. ```nmrsim```
· What it does: An open source python library that contains many functions for the design, synthetic development, and display of NMR spectra data.
· Inputs: See README for more details on the functions
· Outputs: Synthetic or experimental NMR data as plots or raw array data
· Interactions: User/ML tech would import this library to generate or interact with NMR spectra on the local machine
2. ```authenticate```
· What it does: Prompted to make edits to the code, user inputs a user and password that would grant them access to make changes to the software
· Inputs: Username and password
· Outputs: Access
· Interactions: User inputs a username and password
3. ```model.py```
· What it does: An output of the training of the machine learning model that can be imported to future notebooks or environments for ML predictions from experimental data
· Inputs: Directory for where experimental data is stored
· Outputs: A model for ML and an upscaled NMR spectra
· Interactions: User can specify what model (100, 200, 300 Mhz etc)
4. ```model.pkl```
· What it does: A saved model for each upscale resolution (may need multiple models). Pretrained from model.py
· Inputs: Prediction data, takes new nmr data and makes a model prediction for new data
· Outputs: model prediction as an NMR spectrum
· Interactions: user calls this on some interface
5. ```import_new_data```
· What it does: Allows a user to import new experimental data from a local repository
· Inputs: Experimental NMR spectra (in csv format?)
· Output: Numpy arrays for each new spectrum that can be input to a prediction model
· Interactions: User calls this function to import their data, specificying the file that needs imported
Extra
1. Machine Learning Technician
· Markdown, for tracking/describing file structures, functions, what things do, etc.. Good software engineering practices
· Docstrings i.e. define in detail what functions do
· Frequent comments on code
· Changelog?
· Descriptive commit messages for our own sanity
2. Lab Tech (Basic User, Data In/Data Out)
· Example use case
· Manual
· What functions, data types
· Collection of potential error messages
· FAQ
· Resources/contacts, feedback mechanism/email
· Interactive UI
3. Resource Tracking
· Statistics for ML Performance
· Stats for usage (users, # times used, failure tracking for UI)
4. Communication with Outside Software

## User interactiveity with code
Is there a difference if the user will use a notebook (jupyter/colab) or use the bash / coman line? | streamline Nels
how is the user going to interacte with our code/software? | Give the code the file ( file path) |  | Give the code the name of the column | Cmponent will use the information to the code |  | Produce enhanced resolution |  | Save the new csv file with 60 and 400 MHz and produce a visualization
How can we upload the trained model | How can I save the training model | I'm I saving parameter/hyperparamets | Do i need to remove the other models from our repo? | **Save the model as we're training using early stop | torch.save/ check pointing | https://medium.com/pytorch/using-optuna-to-optimize-pytorch-hyperparameters-990607385e36 | optuna-examples/pytorch_checkpoint.py at main · optuna/optuna-examples · GitHub
For data training on Hyak… can I | Create data, save it and use it for training